## Sheet 1
S.No. | Element Name | Req Shutdown Range | RPC Status | RPC ShutDown Range | RPC Remarks | Reason | D-3 Req Date
1 | 125 MVAR BUS REACTOR NO 1 AT 400KV PHAGI(RS) | 02-09-2022 08:00 - 02-09-2022 18:00 | Approved | 02-09-2022 08:00 - 02-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 30.08.2022
2 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 02-09-2022 17:00 - 02-09-2022 23:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 30.08.2022
3 | 400/220 KV 315 MVA ICT 1 AT BARMER(RS) | 02-09-2022 08:00 - 02-09-2022 18:00 | Approved | 02-09-2022 08:00 - 02-09-2022 18:00 |  | Quarterly Maintenance | 30.08.2022
4 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 02-09-2022 17:00 - 02-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 30.08.2022
5 | 412 MAIN BAY - 400KV AKAL-JODHPUR (RS) CKT-1 AT JODHPUR(RS) | 02-09-2022 08:00 - 16-09-2022 18:00 | Approved | 02-09-2022 08:00 - 16-09-2022 18:00 |  | Replacement of circuit breaker (Bus B side breaker 852B CB of 400kV Jodhpur-Akal line at jodhpur end) Line will remain in service with 852 A CB. | 30.08.2022
6 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 03-09-2022 17:00 - 03-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 31.08.2022
7 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 03-09-2022 17:00 - 03-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 31.08.2022
8 | 400 KV HEERAPURA-HINDAUN (RS) CKT-1 | 01-09-2022 08:00 - 18-09-2022 18:00 | Approved | 03-09-2022 08:00 - 15-09-2022 18:00 | Rajasthan has to maintain voltage at Hindaun/Inspector clearance required. | Completion of raising / shifting work of above line at tower/Loc. No.307 to 308 (channel No.191+650) | 31.08.2022
9 | 220 KV BASSI(PG)-BAGRU(RS) (PG) CKT-1 | 04-09-2022 08:00 - 04-09-2022 18:00 | Approved | 04-09-2022 08:00 - 04-09-2022 18:00 |  | For quarterly maintenance work of whole grid sub-station | 01.09.2022
10 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 04-09-2022 08:00 - 04-09-2022 18:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 01.09.2022
11 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 04-09-2022 08:00 - 04-09-2022 18:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 01.09.2022
12 | 400 KV CHHABRA-CHHABRA SCTPS (RS) CKT-1 | 05-09-2022 08:00 - 06-09-2022 18:00 | Approved | 05-09-2022 08:00 - 05-09-2022 18:00 | May be given on Daily Basis | For tightening of Bay equipments & Relay testing | 02.09.2022
13 | 400KV BUS 1KANKANI(RS) | 05-09-2022 08:00 - 05-09-2022 18:00 | Approved | 05-09-2022 08:00 - 05-09-2022 18:00 |  | Preventive Maintenance work of 400 KV Main Bus-I | 02.09.2022
14 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 05-09-2022 17:00 - 05-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 02.09.2022
15 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 05-09-2022 17:00 - 05-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 02.09.2022
16 | 400/11 KV 80 MVA ST 2 AT KAWAI SCTPS(APR) | 05-09-2022 08:00 - 07-09-2022 18:00 | Approved | 05-09-2022 08:00 - 07-09-2022 18:00 |  | Annual maintenance and testing of station transformer#2 & bay equipments. | 02.09.2022
17 | 400/220 KV 315 MVA ICT 1 AT ALWAR(ATIL) | 05-09-2022 09:30 - 05-09-2022 14:00 | Approved | 05-09-2022 09:30 - 05-09-2022 14:00 |  | For CSD(Control Switch device) Online Testing. | 02.09.2022
18 | 400 KV JODHPUR-KANKANI (RS) CKT-1 | 06-09-2022 08:00 - 06-09-2022 18:00 | Approved | 06-09-2022 08:00 - 06-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work of line | 03.09.2022
19 | 125 MVAR BUS REACTOR NO 1 AT 400KV MERTA(RS) | 06-09-2022 08:00 - 06-09-2022 18:00 | Approved | 06-09-2022 08:00 - 06-09-2022 18:00 |  | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 03.09.2022
20 | 400/220 KV 315 MVA ICT 2 AT BARMER(RS) | 06-09-2022 08:00 - 06-09-2022 18:00 | Approved | 06-09-2022 08:00 - 06-09-2022 18:00 |  | Quarterly Maintenance | 03.09.2022
21 | 400KV BUS 1 AT PHAGI(RS) | 06-09-2022 08:00 - 06-09-2022 18:00 | Approved | 06-09-2022 08:00 - 06-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 03.09.2022
22 | 400 KV CHHABRA-CHHABRA SCTPS (RS) CKT-1 | 05-09-2022 08:00 - 06-09-2022 18:00 | Approved | 06-09-2022 08:00 - 06-09-2022 18:00 | May be given on Daily Basis | For tightening of Bay equipments & Relay testing | 03.09.2022
23 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 06-09-2022 17:00 - 06-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 03.09.2022
24 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 06-09-2022 17:00 - 06-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 03.09.2022
25 | 220 KV CHARKHI DADRI(BB)-KHETRI(RS) (BB) CKT-2 | 06-09-2022 08:00 - 09-09-2022 18:00 | Approved | 06-09-2022 08:00 - 09-09-2022 18:00 | May be given subject to Rajasthan consent | For replacement of Main bus isloator at 220KV GSS BBMB Dadri | 03.09.2022
26 | 400/220 KV 315 MVA ICT 2 AT ALWAR(ATIL) | 06-09-2022 09:30 - 06-09-2022 14:00 | Approved | 06-09-2022 09:30 - 06-09-2022 14:00 |  | For CSD(Control Switch device) Online Testing. | 03.09.2022
27 | 400 KV BIKANER(PG)-BIKANER(RS) (PG) CKT-1 | 06-09-2022 18:00 - 06-09-2022 22:00 | Approved | 06-09-2022 17:00 - 06-09-2022 22:00 |  | Routine Maintenance | 03.09.2022
28 | 40452T TIE BAY - 400/220 KV 315 MVA ICT 1 AT JODHPUR(RS) (RRVPNL) AND 400 KV JODHPUR-KANKANI (RS) CKT-1 AT 400 KV JODHPUR(RS) (RRVPNL) | 07-09-2022 08:00 - 07-09-2022 18:00 | Approved | 07-09-2022 08:00 - 07-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 04.09.2022
29 | 400 KV KOTA(PG)-MERTA(RS) (PG) CKT-1 | 07-09-2022 08:00 - 07-09-2022 18:00 | Approved | 07-09-2022 08:00 - 07-09-2022 18:00 |  | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 04.09.2022
30 | 400 KV ANTA-KALISINDH (RS) CKT-2 | 07-09-2022 08:00 - 07-09-2022 18:00 | Approved | 07-09-2022 08:00 - 07-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 04.09.2022
31 | 400/220 KV 500 MVA ICT 1 AT BHILWARA(RS) | 07-09-2022 08:00 - 07-09-2022 18:00 | Approved | 07-09-2022 08:00 - 07-09-2022 18:00 |  | Routine Maintenance and Testing of 500 MVA 400/220/33 KV Transformer No.1 and Bay (4152A) & Associated Equipments | 04.09.2022
32 | 400 KV CHHABRA-CHHABRA SCTPS (RS) CKT-2 | 07-09-2022 08:00 - 08-09-2022 18:00 | Approved | 07-09-2022 08:00 - 07-09-2022 18:00 | May be given on Daily Basis | For tightening of Bay equipments & Relay testing | 04.09.2022
33 | 220 KV BASSI(PG)-INDIRA NAGAR(RS) (PG) CKT-1 | 07-09-2022 08:00 - 07-09-2022 18:00 | Approved | 07-09-2022 08:00 - 07-09-2022 18:00 |  | Quartererly maintenance of Bay Equipment | 04.09.2022
34 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 07-09-2022 17:00 - 07-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 04.09.2022
35 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 07-09-2022 17:00 - 07-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 04.09.2022
36 | 400 KV SHREE CEMENT(SCL)-MERTA(RS) (PG) CKT-1 | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 05.09.2022
37 | 400 KV ANTA-KALISINDH (RS) CKT-1 | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 05.09.2022
38 | 400KV BUS 1 AT BARMER(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Quarterly Maintenance | 05.09.2022
39 | 50 MVAR BUS REACTOR NO 1 AT 400KV RATANGARH(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 05.09.2022
40 | 400 KV RAJWEST(RW)-KANKANI (RS) CKT-1 | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Planned maintenance | 05.09.2022
41 | 400KV BUS 2 AT PHAGI(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 05.09.2022
42 | 400KV BUS 2KANKANI(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Preventive Maintenance work of 400 KV Main Bus-II | 05.09.2022
43 | 400KV BUS 1 AT BHILWARA(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Half Yearly Maintenance of 400KV Main Bus-1 and Associated Equipments | 05.09.2022
44 | 220 KV INDIRA NAGAR(RS)-HEERAPURA(RS) (PG) CKT-1 | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Quartererly maintenance of Bay Equipment | 05.09.2022
45 | 400 KV BHILWARA(RS)-CHHABRA(RVUN) (RS) CKT-1 | 08-09-2022 08:00 - 09-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 | May be given on Daily Basis | On 8th sept Shutdown is required at both end (alongwith line reactor at Bhilwara end)for maintenance. and on 22nd Sept for CTPP end.Shutdown is required at both end for maintenance. and on 13th Sept for CTPP end.1. For annual maintanence of Switchyard Equipments at CTPP End | 05.09.2022
46 | 400/220 KV 315 MVA ICT 1 AT BABAI(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Quarterly Maintenance | 05.09.2022
47 | 403 MAIN BAY - 400/220KV 315 MVA ICT 1 AT JODHPUR(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 05.09.2022
48 | 400/220 KV 315 MVA ICT 1 AT BIKANER(RS) | 08-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 |  | Routine Maintenance | 05.09.2022
49 | 400 KV CHHABRA-CHHABRA SCTPS (RS) CKT-2 | 07-09-2022 08:00 - 08-09-2022 18:00 | Approved | 08-09-2022 08:00 - 08-09-2022 18:00 | May be given on Daily Basis | For tightening of Bay equipments & Relay testing | 05.09.2022
50 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 08-09-2022 17:00 - 08-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 05.09.2022
51 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 08-09-2022 17:00 - 08-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 05.09.2022
52 | 220 KV ANTA(NT)-LALSOTE(RS) (PG) CKT-1 | 08-09-2022 09:30 - 08-09-2022 15:30 | Approved | 08-09-2022 09:30 - 08-09-2022 15:30 |  | Quarterly maintenance work | 05.09.2022
53 | 220 KV LALSOTE(RS)-DAUSA(RS) (PG) CKT-1 | 08-09-2022 09:30 - 08-09-2022 15:30 | Approved | 08-09-2022 09:30 - 08-09-2022 15:30 |  | Quarterly maintenance work | 05.09.2022
54 | 400KV BUS 1 AT KAWAI SCTPS(APR) | 09-09-2022 08:00 - 10-09-2022 18:00 | Approved | 09-09-2022 08:00 - 09-09-2022 18:00 | May be given on Daily Basis | Annual maintenance & testing of 400 KV Bus - 1 connecting isolators. | 06.09.2022
55 | 400 KV AKAL-RAMGARH (RS) CKT-1 | 09-09-2022 08:00 - 09-09-2022 18:00 | Approved | 09-09-2022 08:00 - 09-09-2022 18:00 |  | Quarterly Maintenance | 06.09.2022
56 | 400 KV RAJWEST(RW)-JODHPUR (RS) CKT-1 | 09-09-2022 08:00 - 09-09-2022 18:00 | Approved | 09-09-2022 08:00 - 09-09-2022 18:00 |  | Planned maintenance at Rajwest end and Quaterly Preventive Maintenance and testing work of line alongwith 400 KV LINE REACTOR at Jodhpur end and | 06.09.2022
57 | 400 KV BHILWARA(RS)-CHHABRA(RVUN) (RS) CKT-1 | 08-09-2022 08:00 - 09-09-2022 18:00 | Approved | 09-09-2022 08:00 - 09-09-2022 18:00 | May be given on Daily Basis | On 8th sept Shutdown is required at both end (alongwith line reactor at Bhilwara end)for maintenance. and on 22nd Sept for CTPP end.Shutdown is required at both end for maintenance. and on 13th Sept for CTPP end.1. For annual maintanence of Switchyard Equipments at CTPP End | 06.09.2022
58 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 09-09-2022 17:00 - 09-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 06.09.2022
59 | 400 KV BIKANER-BHADLA (RS) CKT-1 | 02-09-2022 08:00 - 09-09-2022 18:00 | Approved | 09-09-2022 17:00 - 09-09-2022 22:00 | Could be given on Daily basis after 1700 Hrs | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 06.09.2022
60 | 400 KV BARMER(RS)-RAJWEST(RW) (RS) CKT-1 | 10-09-2022 08:00 - 10-09-2022 18:00 | Approved | 10-09-2022 08:00 - 10-09-2022 18:00 |  | Quarterly Maintenance at both end | 07.09.2022
61 | 400KV BUS 2 AT JODHPUR(RS) | 10-09-2022 08:00 - 10-09-2022 18:00 | Approved | 10-09-2022 08:00 - 10-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 07.09.2022
62 | 400 KV AKAL-RAMGARH (RS) CKT-2 | 10-09-2022 08:00 - 10-09-2022 18:00 | Approved | 10-09-2022 08:00 - 10-09-2022 18:00 |  | Quarterly Maintenance | 07.09.2022
63 | 400KV BUS 1 AT KAWAI SCTPS(APR) | 09-09-2022 08:00 - 10-09-2022 18:00 | Approved | 10-09-2022 08:00 - 10-09-2022 18:00 | May be given on Daily Basis | Annual maintenance & testing of 400 KV Bus - 1 connecting isolators. | 07.09.2022
64 | 400/220 KV 500 MVA ICT 2 AT BHADLA(RS) | 10-09-2022 16:00 - 10-09-2022 22:00 | Approved | 10-09-2022 16:00 - 10-09-2022 22:00 | May be taken after 1700 Hrs | Quarterly Maintenance work at 400KV GSS Bhadla | 07.09.2022
65 | 400/220 KV 500 MVA ICT 3 AT BHADLA(RS) | 11-09-2022 16:00 - 11-09-2022 22:00 | Approved | 11-09-2022 16:00 - 11-09-2022 22:00 | May be taken after 1700 Hrs | Quarterly Maintenance work at 400KV GSS Bhadla | 08.09.2022
66 | 400 KV AJMER(RS)-AJMER(PG) (PG) CKT-2 | 12-09-2022 08:00 - 12-09-2022 18:00 | Approved | 12-09-2022 08:00 - 12-09-2022 18:00 |  | Half Yearly maintenance & Testing work of associated equipments of 400 KV Ajmer-Ajmer (PG) Ckt-II Line & Bay (419) & TIE bay 400 KV Ajmer-Ajmer (PG) Ckt-II (420) to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 09.09.2022
67 | 70152A MAIN BAY - 765KV PHAGI(RS)-BHIWANI(PG) (PG) CKT-2 AT PHAGI(RS) | 12-09-2022 08:00 - 12-09-2022 18:00 | Approved | 12-09-2022 08:00 - 12-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 09.09.2022
68 | 400KV BUS 2 AT KAWAI SCTPS(APR) | 12-09-2022 08:00 - 13-09-2022 18:00 | Approved | 12-09-2022 08:00 - 12-09-2022 18:00 | May be given on Daily Basis | Annual maintenance & testing of 400 KV Bus - 1 connecting isolators. | 09.09.2022
69 | 400 KV ANTA-CHHABRA (RS) CKT-1 | 12-09-2022 08:00 - 13-09-2022 18:00 | Approved | 12-09-2022 08:00 - 12-09-2022 18:00 | May be given on Daily Basis | On 12th Sept Shutdown is required at both end for maintenance. and on 13th Sept for CTPP end.1. For annual maintanence of Switchyard Equipments at CTPP End. 2. Annual Relay Testing at CTPP End. | 09.09.2022
70 | 400 KV BHADLA-RAMGARH (RS) CKT-1 | 12-09-2022 08:00 - 12-09-2022 18:00 | Approved | 12-09-2022 08:00 - 12-09-2022 18:00 | May be taken after 1700 Hrs | Quarterly Maintenance | 09.09.2022
71 | 400/220 KV 500 MVA ICT 1 AT BHADLA(RS) | 12-09-2022 16:00 - 12-09-2022 22:00 | Approved | 12-09-2022 16:00 - 12-09-2022 22:00 | May be taken after 1700 Hrs | Quarterly Maintenance work at 400KV GSS Bhadla | 09.09.2022
72 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | 12-09-2022 18:00 - 12-09-2022 23:00 | Approved | 12-09-2022 18:00 - 12-09-2022 23:00 | May be taken after 1700 Hrs | Quaterly Preventive Maintenance and testing work. | 09.09.2022
73 | 400 KV ANTA(RS)-KOTA(PG) (RS) CKT-1 | 13-09-2022 08:00 - 13-09-2022 18:00 | Approved | 13-09-2022 08:00 - 13-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 10.09.2022
74 | 220 KV CHARKHI DADRI(BB)-KHETRI(RS) (BB) CKT-1 | 13-09-2022 08:00 - 13-09-2022 18:00 | Approved | 13-09-2022 08:00 - 13-09-2022 18:00 |  | For quartely maintenance & Tree Trimming under the Line requiring Shutdown | 10.09.2022
75 | 400 KV AJMER(RS)-AJMER(PG) (PG) CKT-1 | 13-09-2022 08:00 - 13-09-2022 18:00 | Approved | 13-09-2022 08:00 - 13-09-2022 18:00 |  | Half Yearly maintenance & Testing work of associated equipments of 400 KV Ajmer-Ajmer (PG) Ckt-I Line & Bay (422) & TIE bay 400 KV Ajmer-Ajmer (PG) Ckt-I (423) to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 10.09.2022
76 | 400 KV ANTA-CHHABRA (RS) CKT-1 | 12-09-2022 08:00 - 13-09-2022 18:00 | Approved | 13-09-2022 08:00 - 13-09-2022 18:00 | May be given on Daily Basis | On 12th Sept Shutdown is required at both end for maintenance. and on 13th Sept for CTPP end.1. For annual maintanence of Switchyard Equipments at CTPP End. 2. Annual Relay Testing at CTPP End. | 10.09.2022
77 | 400KV BUS 2 AT KAWAI SCTPS(APR) | 12-09-2022 08:00 - 13-09-2022 18:00 | Approved | 13-09-2022 08:00 - 13-09-2022 18:00 | May be given on Daily Basis | Annual maintenance & testing of 400 KV Bus - 1 connecting isolators. | 10.09.2022
78 | 400/220 KV 315 MVA ICT 2 AT BIKANER(RS) | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 |  | Routine Maintenance | 11.09.2022
79 | 400 KV BHADLA-RAMGARH (RS) CKT-2 | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 | May be taken after 1700 Hrs | Quarterly Maintenance | 11.09.2022
80 | 400KV BUS 2 AT BHILWARA(RS) | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 |  | Half Yearly Maintenance of 400KV Main Bus-2 and Associated Equipments | 11.09.2022
81 | 70252A MAIN BAY - 765 KV PHAGI(RS)-BHIWANI(PG) (PG) CKT-1 AT PHAGI(RS) | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 11.09.2022
82 | 406 MAIN BAY - 400/220KV 315 MVA ICT 2 AT JODHPUR(RS) | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 11.09.2022
83 | 400 KV AJMER-BHILWARA (RS) CKT-1 | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 |  | Routine Maintenane and testing of 4400 KV AJMER -BHILWARA CKT-1 BAY(4152B)& ASSOCIATED EQUIPMENTS | 11.09.2022
84 | 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-1 | 14-09-2022 08:00 - 15-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 | May be given on Daily Basis | 1. NABL Calibration of line metering CT's and Energy meters. 2.Annual maintenance and testing of Line/Bay equipments. | 11.09.2022
85 | 400KV BUS 1 AT AJMER(RS) | 14-09-2022 08:00 - 14-09-2022 18:00 | Approved | 14-09-2022 08:00 - 14-09-2022 18:00 |  | Half Yearly maintenance & Testing work of associated equipments of 400 KV Main Bus-I to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 11.09.2022
86 | 220 KV BADARPUR(NT)-ALWAR MIA(RS) (RS) CKT-1 | 14-09-2022 08:00 - 18-09-2022 18:00 | Approved | 14-09-2022 08:00 - 18-09-2022 18:00 |  | For Bay / Line maintenance & tree trimming work under line | 11.09.2022
87 | 400KV BUS 1 AT ANTA(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 12.09.2022
88 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 12.09.2022
89 | 400/220 KV 315 MVA ICT 2 AT JODHPUR(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 12.09.2022
90 | 400/220 KV 315 MVA ICT 3 AT AJMER(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Since the Tie bay has not been commissioned therefore 315 MVA, 400/220 KV Kanohar make ICT-III shall remain 'Off' during S/D Period of 400 KV Main Bus-II & load will be fed by 400 /220 KV ICT-I. | 12.09.2022
91 | 400KV BUS 2 AT AJMER(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Half Yearly maintenance & Testing work of associated equipments of 400 KV Main Bus-I to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 12.09.2022
92 | 220 KV AGRA(PG)-BHARATPUR(RS) (PG) CKT-1 | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | For bay and line maintenance work | 12.09.2022
93 | 400 KV PHAGI-AJMER (RS) CKT-2 | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | 400 KV Ajmer - Phagi Ckt-II Line will remain "OFF" due to defective Main Circuit breaker during S/D Period of 400 KV Main Bus-II | 12.09.2022
94 | 220 KV BASSI(PG)-DAUSA(RS) (PG) CKT-1 | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Quarterly maintenance work | 12.09.2022
95 | 400KV BUS 2 AT BABAI(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Quarterly Maintenance | 12.09.2022
96 | 400KV BUS 1 AT RATANGARH(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 12.09.2022
97 | 220 KV MODAK(RS)-BHANPURA(MP) (MPSEB) CKT-1 | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 | Subjected to consent from Rajasthan | For Halfyearly maintenance work | 12.09.2022
98 | 80 MVAR BUS REACTOR NO 1 AT 400 KV BABAI(RS) | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Quarterly Maintenance | 12.09.2022
99 | 400 KV JAISALMER-BARMER (RS) CKT-1 | 15-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 |  | Quarterly Maintenance | 12.09.2022
100 | 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-1 | 14-09-2022 08:00 - 15-09-2022 18:00 | Approved | 15-09-2022 08:00 - 15-09-2022 18:00 | May be given on Daily Basis | 1. NABL Calibration of line metering CT's and Energy meters. 2.Annual maintenance and testing of Line/Bay equipments. | 12.09.2022
101 | 70552A MAIN BAY - 240 MVAR BUS REACTOR NO 1 AT 765KV PHAGI(RS) | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 13.09.2022
102 | 400KV BUS 2 AT ANTA(RS) | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 13.09.2022
103 | 400KV BUS 1 AT JODHPUR(RS) | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 13.09.2022
104 | 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-2 | 16-09-2022 08:00 - 17-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 | May be given on Daily Basis | For both end.1. NABL Calibration of line metering CT's and Energy meters. 2.Annual maintenance and testing of Line/Bay equipments. | 13.09.2022
105 | 132 KV AMARPURATHEDI(RS)-HISAR(BB) (RS) CKT-1 | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | for Quarterly Maintenance | 13.09.2022
106 | 400 KV SIKAR(PG)-BABAI(RS) (NRSS36) CKT-1 | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | Quarterly Maintenance | 13.09.2022
107 | 220 KV AGRA(PG)-SIKANDRA(UP) (PG) CKT-1 | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | For line maintenance work | 13.09.2022
108 | 400/220 KV 500 MVA ICT 2 AT RAMGARH(RS) | 16-09-2022 08:00 - 16-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | Quarterly Maintenance | 13.09.2022
109 | 400 KV AKAL-JODHPUR (RS) CKT-1 | 16-09-2022 08:00 - 17-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 |  | On 16.09.2022 Shutdown of Bus -A (Tie breaker is not available) and line bay maintenance on 17.09.2022 | 13.09.2022
110 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 16-09-2022 08:00 - 16-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 13.09.2022
111 | 400 KV JAISALMER-BARMER (RS) CKT-2 | 17-09-2022 08:00 - 17-09-2022 18:00 | Approved | 17-09-2022 08:00 - 17-09-2022 18:00 |  | Quarterly Maintenance | 14.09.2022
112 | 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-2 | 16-09-2022 08:00 - 17-09-2022 18:00 | Approved | 17-09-2022 08:00 - 17-09-2022 18:00 | May be given on Daily Basis | For both end.1. NABL Calibration of line metering CT's and Energy meters. 2.Annual maintenance and testing of Line/Bay equipments. | 14.09.2022
113 | 400 KV AKAL-JODHPUR (RS) CKT-1 | 16-09-2022 08:00 - 17-09-2022 18:00 | Approved | 17-09-2022 08:00 - 17-09-2022 18:00 |  | On 16.09.2022 Shutdown of Bus -A (Tie breaker is not available) and line bay maintenance on 17.09.2022 | 14.09.2022
114 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 17-09-2022 08:00 - 17-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 14.09.2022
115 | 400/220 KV 500 MVA ICT 1 AT RAMGARH(RS) | 18-09-2022 08:00 - 18-09-2022 18:00 | Approved | 18-09-2022 08:00 - 18-09-2022 18:00 |  | Quarterly Maintenance | 15.09.2022
116 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 18-09-2022 08:00 - 18-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 15.09.2022
117 | 400 KV CHHABRA(RVUN)-KAWAI SCTPS(APR) (RS) CKT-1 | 19-09-2022 08:00 - 20-09-2022 18:00 | Approved | 19-09-2022 08:00 - 19-09-2022 18:00 | May be given on Daily Basis | 1. NABL Calibration of line metering CTs and Energy meters. 2.Annual maintenance and testing of Line/Bay equipments. | 16.09.2022
118 | 765KV BUS 1 AT ANTA(RS) | 19-09-2022 08:00 - 19-09-2022 18:00 | Approved | 19-09-2022 08:00 - 19-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 16.09.2022
119 | 400 KV JODHPUR-KANKANI (RS) CKT-2 | 19-09-2022 08:00 - 19-09-2022 18:00 | Approved | 19-09-2022 08:00 - 19-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work of line alongwith LINE REACTOR at Jodhpur. | 16.09.2022
120 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 19-09-2022 08:00 - 19-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 16.09.2022
121 | 405 TIE BAY - 400/220KV 315 MVA ICT 2 AT JODHPUR(RS) AND 400KV BHADLA(RS)-JODHPUR(RS) (UNDEF) CKT-1 | 19-09-2022 08:00 - 15-10-2022 18:00 | Approved | 19-09-2022 08:00 - 24-09-2022 18:00 | Outage duration could be restricted for 5-6 Days | Replacement of circuit breaker | 16.09.2022
122 | 400KV BUS 1 AT RAMGARH(RS) | 20-09-2022 08:00 - 20-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 |  | Quarterly Maintenance | 17.09.2022
123 | 765KV BUS 2 AT ANTA(RS) | 20-09-2022 08:00 - 20-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 |  | HALF YEARLY MAINTENANCE | 17.09.2022
124 | 400 KV AKAL-BARMER (RS) CKT-1 | 20-09-2022 08:00 - 20-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 |  | Quarterly Maintenance | 17.09.2022
125 | 400 KV ALWAR(ATIL)-HINDAUN(RS) (ATIL) CKT-1 | 20-09-2022 08:00 - 20-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 |  | Quarterly and Half yearly Maintenance work | 17.09.2022
126 | 70252T TIE BAY - 765KV PHAGI(RS)-BHIWANI(PG) (PG) CKT-1 AND 765/400KV 1500 MVA ICT 2 AT PHAGI(RS) | 20-09-2022 08:00 - 20-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 17.09.2022
127 | 400 KV CHHABRA(RVUN)-KAWAI SCTPS(APR) (RS) CKT-1 | 19-09-2022 08:00 - 20-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 | May be given on Daily Basis | 1. NABL Calibration of line metering CTs and Energy meters. 2.Annual maintenance and testing of Line/Bay equipments. | 17.09.2022
128 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 17.09.2022
129 | 400/220 KV 315 MVA ICT 1 AT DEEDWANA(MTS) | 20-09-2022 11:00 - 20-09-2022 14:00 | Approved | 20-09-2022 11:00 - 20-09-2022 14:00 |  | For CSD commissioning (Control Switch device) & Online Testing. | 17.09.2022
130 | 400 KV CIRCUIT BREAKER 952T of 400 KV KANKANI-II BAY at 400kV GSS Jodhpur | 20.09.2022 | Approved | 20-09-2022 08:00 - 20-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 17.09.2022
130 | 400/220 KV 315 MVA ICT 1 AT JODHPUR(RS) | 21-09-2022 08:00 - 21-09-2022 18:00 | Approved | 21-09-2022 08:00 - 21-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 18.09.2022
131 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 21-09-2022 08:00 - 21-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 18.09.2022
132 | 400 KV HINDAUN(RS)-CHHABRA(RVUN) (RS) CKT-1 | 21-09-2022 08:00 - 22-09-2022 18:00 | Approved | 21-09-2022 08:00 - 22-09-2022 18:00 |  | On 21st sept Shutdown is required at both end for maintenance. and on 22nd Sept for CTPP end.1. For annual maintanence of Switchyard Equipments at CTPP End1. For annual maintanence of Switchyard Equipments at CTPP End. 2. Annual Relay Testing at CTPP End. | 18.09.2022
133 | 400/220 KV 315 MVA ICT 2 AT DEEDWANA(MTS) | 21-09-2022 11:00 - 21-09-2022 14:00 | Approved | 21-09-2022 11:00 - 21-09-2022 14:00 |  | For CSD commissioning (Control Switch device) & Online Testing. | 18.09.2022
134 | 400 KV NEEMRANA(PG)-BABAI(RS) (NRSS36) CKT-1 | 22-09-2022 08:00 - 22-09-2022 15:00 | Approved | 22-09-2022 08:00 - 22-09-2022 15:00 |  | Quarterly Maintenance | 19.09.2022
135 | 220 KV ANTA(NT)-SAWAIMADHOPUR(RS) (PG) CKT-1 | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | For Half yearly Maintenance at 220kV GSS SWM | 19.09.2022
136 | 400KV BUS 2 AT RAMGARH(RS) | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | Quarterly Maintenance | 19.09.2022
137 | 70552T TIE BAY - 240 MVAR BUS REACTOR NO 1 AT 765KV PHAGI(RS) (POWERGRID) AND 765 KV AJMER(PG)-PHAGI(RS) (PG) CKT-1 AT 765 KV PHAGI(RS) (POWERGRID) | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 19.09.2022
138 | 220 KV ANTA(NT)-SAKATPURA(RS) (RS) CKT-1 | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 19.09.2022
139 | 220 KV HISSAR(BB)-CHIRAWA(RS) (BB) CKT-1 | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | For quartely maintenance & Tree Trimming under the Line requiring Shutdown | 19.09.2022
140 | 400/220 KV 315 MVA ICT 1 AT HINDAUN(RS) | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | Quarterly and Half yearly Maintenance work | 19.09.2022
141 | 400 KV BHINMAL(PG)-BARMER(RS) (RS) CKT-1 | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | Quarterly Maintenance | 19.09.2022
142 | 400KV BUS 2 AT RATANGARH(RS) | 22-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 19.09.2022
143 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | 15-09-2022 08:00 - 22-09-2022 18:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 | May be given subject to all necessary CEA clearances | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 19.09.2022
144 | 63 MVAR BUS REACTOR NO 1 AT 400 KV KAWAI SCTPS(APR) | 22-09-2022 08:00 - 26-09-2022 18:00 | Approved | 22-09-2022 08:00 - 26-09-2022 18:00 |  | Annual maintenance and testing of bus reactor#1 & Bay equipments. | 19.09.2022
145 | 50 MVAR BUS REACTOR NO 1 AT 400KV DEEDWANA(MTS) | 22-09-2022 11:00 - 22-09-2022 14:00 | Approved | 22-09-2022 11:00 - 22-09-2022 14:00 |  | For CSD commissioning(Control Switch device) Online Testing. | 19.09.2022
| 400 KV CIRCUIT BREAKER 1052T Tie bay of 400 KV RAJWEST line at 400kV GSS Jodhpur | 22-09-2022 11:00 - 22-09-2022 14:00 | Approved | 22-09-2022 08:00 - 22-09-2022 18:00 |  | Quaterly Preventive Maintenance and testing work. | 19.09.2022
146 | 765 KV ANTA-PHAGI (RS) CKT-2 | 23-09-2022 08:00 - 23-09-2022 18:00 | Approved | 23-09-2022 08:00 - 23-09-2022 18:00 | May be clubbed alongwith unit outage at Chhabra - KaliSindh - Kawai complex | Shutdown is required alongwith line reactor at Anta end. for HALF YEARLY MAINTENANCE | 20.09.2022
147 | 220 KV RAPS_A(NP)-SAKATPURA(RS) (RS) CKT-1 | 23-09-2022 08:00 - 23-09-2022 18:00 | Approved | 23-09-2022 08:00 - 23-09-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 20.09.2022
148 | 125 MVAR BUS REACTOR NO 1 AT 400KV RAMGARH(RS) | 24-09-2022 08:00 - 24-09-2022 18:00 | Approved | 24-09-2022 08:00 - 24-09-2022 18:00 |  | Quarterly Maintenance | 21.09.2022
149 | 400 KV BHINMAL(PG)-BARMER(RS) (RS) CKT-2 | 24-09-2022 08:00 - 24-09-2022 18:00 | Approved | 24-09-2022 08:00 - 24-09-2022 18:00 |  | Quarterly Maintenance | 21.09.2022
150 | 220 KV DEBARI(RS)-RAPS_A(NP) (RS) CKT-1 | 25-09-2022 08:00 - 25-09-2022 18:00 | Approved | 25-09-2022 08:00 - 25-09-2022 18:00 |  | General Maintenance & Tree trimming Work | 22.09.2022
151 | 220 KV RAPS_B(NP)-DEBARI(RS) (PG) CKT-1 | 26-09-2022 08:00 - 26-09-2022 18:00 | Approved | 26-09-2022 08:00 - 26-09-2022 18:00 |  | General Maintenance & Tree trimming Work | 23.09.2022
152 | 400/220 KV 500 MVA ICT 3 AT RAMGARH(RS) | 26-09-2022 08:00 - 26-09-2022 18:00 | Approved | 26-09-2022 08:00 - 26-09-2022 18:00 |  | Quarterly Maintenance | 23.09.2022
153 | 400KV BUS 2 AT BARMER(RS) | 27-09-2022 08:00 - 27-09-2022 18:00 | Approved | 27-09-2022 08:00 - 27-09-2022 18:00 |  | Quarterly Maintenance | 24.09.2022
154 | 70652T TIE BAY - 765KV PHAGI(RS)-GWALIOR(PG) (UNDEF) CKT-1 AND 765KV ANTA-PHAGI (RS) CKT-1 AT PHAGI(RS) | 27-09-2022 08:00 - 27-09-2022 18:00 | Approved | 27-09-2022 08:00 - 27-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 24.09.2022
155 | 40552T TIE BAY - 400KV BASSI(PG)-PHAGI(RS) (PG) CKT-1 AND FUTURE AT PHAGI(RS) | 28-09-2022 08:00 - 28-09-2022 18:00 | Approved | 28-09-2022 08:00 - 28-09-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 25.09.2022
156 | 765 KV ANTA-PHAGI (RS) CKT-1 | 28-09-2022 08:00 - 29-09-2022 18:00 | Approved | 28-09-2022 08:00 - 29-09-2022 18:00 | May be clubbed alongwith unit outage at Chhabra - KaliSindh - Kawai complex | Shutdown is required alongwith line reactor at Anta end. For Repair & Replacement the damage Conductor at Tower Loc 145-146(D) and attend the Jumper at Tower Loc 239-240 at Railway Crossing. AND HALF YEARLY MAINTENANCE AT GSS | 25.09.2022
157 | 125 MVAR BUS REACTOR NO 1 AT 400KV BARMER(RS) | 29-09-2022 08:00 - 29-09-2022 18:00 | Approved | 29-09-2022 08:00 - 29-09-2022 18:00 |  | Quarterly Maintenance | 26.09.2022
158 | 220 KV RAPS_B(NP)-SAKATPURA(RS) (RS) CKT-1 | 29-09-2022 08:00 - 29-09-2022 18:00 | Approved | 29-09-2022 08:00 - 29-09-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 26.09.2022
159 | 220 KV RAPS_A(NP)-SAKATPURA(RS) (RS) CKT-2 | 30-09-2022 08:00 - 30-09-2022 18:00 | Approved | 30-09-2022 08:00 - 30-09-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 27.09.2022