## Sheet 1
Shutdown No | Element Name | RPC Status | RPC ShutDown Range | RPC Remarks | Reason | D-3 Req
RQ105562 | 400 KV SURATGARH(RVUN)-BIKANER(RS) (RS) CKT-1 | Approved | 01-10-2022 08:00 - 15-10-2022 18:00 | Subject to necessary CEA compliance | Shutdown for Shifting/Modification work at tower location 222 to 224 of 400 kV S/C Bikaner-STPS Line. (Under deposit work of NHAI Supervison by RVPNL) | 28.09.2022
RQ105566 | 400 KV HEERAPURA-HINDAUN (RS) CKT-1 | Approved | 01-10-2022 08:00 - 18-10-2022 18:00 | Subect to revival of Chaabra-Hindaun/CEA compliance | Completion of raising / shifting work of above line at tower/Loc. No.307 to 308 (channel No.191+650) | 28.09.2022
RQ105556 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 04-10-2022 17:00 - 12-10-2022 23:00 |  | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 01.10.2022
RQ105557 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 04-10-2022 17:00 - 12-10-2022 23:00 |  | As per patrolling report of M/s Ramelex Pvt Ltd Pune for the M/o June-2022 Jumper Nut Bolt Missing , Loosening , Need to be Tightened at various Locations | 01.10.2022
RQ104829 | 70652A MAIN BAY - 765KV PHAGI(RS)-GWALIOR(PG) (UNDEF) CKT-1 AT PHAGI(RS) | Approved | 06-10-2022 08:00 - 06-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 03.10.2022
RQ105585 | 400/220 KV 315 MVA ICT 1 AT RATANGARH(RS) | Approved | 06-10-2022 08:00 - 06-10-2022 18:00 |  | Maintenance work of bay equipments , isolators with testing and oil filling | 03.10.2022
RQ105587 | 400/220 KV 315 MVA ICT 2 AT BHILWARA(RS) | Approved | 06-10-2022 08:00 - 06-10-2022 18:00 |  | Routine maintenanceof 315 MVA 400/220/33 KV ICT No.-2 & ASSOCIATED 400KV & 220KV BAY EQUIPMENTS | 03.10.2022
RQ105583 | 400/220 KV 315 MVA ICT 1 AT HINDAUN(RS) | Approved | 06-10-2022 08:00 - 06-10-2022 18:00 |  | Half yearly Maintenance work | 03.10.2022
RQ105589 | 400/11 KV 80 MVA ST 1 AT KAWAI SCTPS(APR) | Approved | 06-10-2022 08:00 - 07-10-2022 18:00 |  | Annual maintenance and testing of station transformer#1 & bay equipments. | 03.10.2022
RQ105602 | 50 MVAR BUS REACTOR NO 1 AT 400KV BHILWARA(RS) | Approved | 07-10-2022 08:00 - 07-10-2022 18:00 |  | Routine maintenance of 400 KV 50MVAR BUS REACTOR BAY (4452A)& ASSOCIATED BAY EQUIPMENTS | 04.10.2022
RQ104827 | 70752A MAIN BAY - 765KV PHAGI(RS)-GWALIOR(PG) (UNDEF) CKT-2 AT PHAGI(RS) | Approved | 07-10-2022 08:00 - 07-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 04.10.2022
RQ105584 | 400/220 KV 315 MVA ICT 2 AT HINDAUN(RS) | Approved | 07-10-2022 08:00 - 07-10-2022 18:00 |  | Half yearly Maintenance work | 04.10.2022
RQ105586 | 400/220 KV 315 MVA ICT 2 AT RATANGARH(RS) | Approved | 08-10-2022 08:00 - 08-10-2022 18:00 |  | Maintenance work of bay equipments , isolators with testing and oil filling | 05.10.2022
RQ105662 | 220 KV HEERAPURA(RS)-I.G.NAGAR(RS) (PG) CKT-1 | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | Quartererly maintenance of Bay Equipment | 07.10.2022
RQ104955 | 765/400 KV 1500 MVA ICT 1 AT ANTA(RS) | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | Quarterly maintenance work | 07.10.2022
RQ105597 | 408 TIE BAY - 63 MVAR BUS REACTOR NO 2 AT 400 KV KAWAI SCTPS(APR) AND 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-2 | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | Annual maintenance and testing of Bay equipments (CB & CT) | 07.10.2022
RQ105596 | 4152T TIE BAY - 400/220 KV 315 MVA ICT 1 AT BHILWARA(RS) AND 400 KV BHILWARA-CHITTORGARH (RS) CKT-2 AT 400 KV BHILWARA(RS) | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | Routine maintenance of 400 KV Tie-1 BAY(4152T)& ASSOCIATED EQUIPMENTS | 07.10.2022
RQ105588 | 400/220 KV 315 MVA ICT 3 AT RATANGARH(RS) | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | Maintenance work of bay equipments , isolators with testing and oil filling | 07.10.2022
RQ105559 | 220 KV AGRA(PG)-SIKANDRA(UP) (PG) CKT-1 | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | For line maintenance work | 07.10.2022
RQ104825 | 70552B MAIN BAY - 765 KV AJMER(PG)-PHAGI(RS) (PAPTL) CKT-1 (PAPTL) AT 765 KV PHAGI(RS) | Approved | 10-10-2022 08:00 - 10-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 07.10.2022
RQ105576 | 400 KV BHILWARA-CHITTORGARH (RS) CKT-1 | Approved | 11-10-2022 08:00 - 11-10-2022 18:00 |  | Routine maintenance of 400 KV Bhilwara-Chittorgarh Ckt-1 Bay & ASSOCIATED BAY EQUIPMENTS | 08.10.2022
RQ105568 | 220 KV ANTA(NT)-SAKATPURA(RS) (RS) CKT-1 | Approved | 11-10-2022 08:00 - 11-10-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 08.10.2022
RQ105661 | 220 KV HEERAPURA(RS)-MANSAROVAR(RS) (PG) CKT-1 | Approved | 11-10-2022 08:00 - 11-10-2022 18:00 |  | Quartererly maintenance of Bay Equipment | 08.10.2022
RQ105553 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | Approved | 11-10-2022 08:00 - 18-10-2022 18:00 | Subject to necessary CEA clearance/PTCC clearance/Rajasthan must ensure supply at Deedwana and other lines healthiness in this complex | Shutdown required for shifting of T/L works due to construction of Nataional Highway Amritsar - Jamnagar T/L under Bharatmala project of PIU - Hanumangarh. | 08.10.2022
RQ105604 | 63 MVAR BUS REACTOR NO 2 AT 400 KV KAWAI SCTPS(APR) | Approved | 12-10-2022 08:00 - 12-10-2022 18:00 |  | Annual maintenance and testing of bus reactor#2 & Isolators. | 09.10.2022
RQ104830 | 70152T TIE BAY - 765KV PHAGI(RS)-BHIWANI(PG) (PG) CKT-2 AND 765/400KV 1500 MVA ICT 1 AT PHAGI(RS) | Approved | 12-10-2022 08:00 - 12-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 09.10.2022
RQ105603 | 80 MVAR BUS REACTOR NO 1 AT 400KV CHITTORGARH(RS) | Approved | 12-10-2022 08:00 - 12-10-2022 18:00 |  | FOR MAINTAINCE WORK of reactor and bay equipments | 09.10.2022
RQ105563 | 400 KV SURATGARH(RVUN)-RATANGARH(RS) (RS) CKT-1 | Approved | 12-10-2022 08:00 - 12-10-2022 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 09.10.2022
RQ105622 | 400 KV RAJWEST(RW)-KANKANI (RS) CKT-1 | Approved | 13-10-2022 08:00 - 13-10-2022 18:00 |  | Planned maintenance | 10.10.2022
RQ105555 | 220 KV DEBARI(RS)-RAPS_A(NP) (RS) CKT-1 | Approved | 13-10-2022 08:00 - 13-10-2022 18:00 |  | General Maintenance & Tree trimming Work | 10.10.2022
RQ104824 | 703B MAIN BAY - 765/400 KV 1500 MVA ICT 3 AT PHAGI(RS) (RRVPNL) AT 765 KV PHAGI(RS) | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 11.10.2022
RQ105554 | 132 KV AMARPURATHEDI(RS)-HISAR(BB) (RS) CKT-1 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | for Quarterly Maintenance | 11.10.2022
RQ105564 | 400 KV SURATGARH(RVUN)-RATANGARH(RS) (RS) CKT-2 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 11.10.2022
RQ105571 | 220 KV RAPS_A(NP)-SAKATPURA(RS) (RS) CKT-1 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 11.10.2022
RQ104957 | 765/400 KV 1500 MVA ICT 2 AT ANTA(RS) | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | Quarterly maintenance work | 11.10.2022
RQ105560 | 220 KV RAPS_B(NP)-DEBARI(RS) (PG) CKT-1 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | General Maintenance & Tree trimming Work | 11.10.2022
RQ105623 | 400 KV RAJWEST(RW)-JODHPUR (RS) CKT-1 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | Planned maintenance | 11.10.2022
RQ104954 | 220 KV MODAK(RS)-BHANPURA(MP) (MPSEB) CKT-1 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 | Subjected to WRPC Consent | Quarterly maintenancework | 11.10.2022
RQ105565 | 220 KV HISSAR(BB)-CHIRAWA(RS) (BB) CKT-1 | Approved | 14-10-2022 08:00 - 14-10-2022 18:00 |  | Tree Trimming, as per govt. norms, under the Line requiring Shutdown | 11.10.2022
RQ105598 | 409 MAIN BAY - 63 MVAR BUS REACTOR NO 2 AT 400 KV KAWAI SCTPS(APR) | Approved | 14-10-2022 08:00 - 16-10-2022 18:00 |  | Annual maintenance and testing of Bay equipments (CB & CT) and Circuit Breaker Overhauling | 11.10.2022
RQ105624 | 400 KV BARMER(RS)-RAJWEST(RW) (RS) CKT-1 | Approved | 15-10-2022 08:00 - 15-10-2022 18:00 |  | Planned maintenance | 12.10.2022
RQ105567 | 400 KV MERTA-RATANGARH (RS) CKT-1 | Approved | 15-10-2022 08:00 - 15-10-2022 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 12.10.2022
RQ105558 | 400 KV BHILWARA-CHITTORGARH (RS) CKT-2 | Approved | 17-10-2022 08:00 - 17-10-2022 18:00 |  | Routine maintenance of 400 KV Bhilwara-Chittorgarh Ckt-2 Bay & ASSOCIATED BAY EQUIPMENTS at both end | 14.10.2022
RQ104826 | 70752T TIE BAY - 765KV PHAGI(RS)-GWALIOR(PG) (UNDEF) CKT-2 AND 765KV ANTA-PHAGI (RS) CKT-2 AT PHAGI(RS) | Approved | 17-10-2022 08:00 - 17-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 14.10.2022
RQ104956 | 765/400 KV 1500 MVA ICT 3 AT ANTA(RS) | Approved | 17-10-2022 08:00 - 17-10-2022 18:00 |  | Quarterly maintenance work | 14.10.2022
RQ105599 | 414 TIE BAY - 400KV CHHABRA(RVUN)-KAWAI SCTPS(APR) (RS) CKT-1 AND FUTURE AT KAWAI SCTPS(APR) | Approved | 17-10-2022 08:00 - 20-10-2022 18:00 |  | Circuit Breaker Overhauling | 14.10.2022
RQ105608 | 400KV BUS 1 AT CHITTORGARH(RS) | Approved | 18-10-2022 08:00 - 18-10-2022 18:00 | Could be taken on Daily Basis | FOR MAINTAINCE AND TESTING WORK | 15.10.2022
RQ105569 | 220 KV CHARKHI DADRI(BB)-KHETRI(RS) (BB) CKT-1 | Approved | 18-10-2022 08:00 - 18-10-2022 18:00 |  | For quartely maintenance & Tree Trimming under the Line requiring Shutdown | 15.10.2022
RQ104823 | 703T TIE BAY - 765/400 KV 1500 MVA ICT 3 AT PHAGI(RS) (RRVPNL) AND FUTURE AT 765 KV PHAGI(RS) (RRVPNL) | Approved | 19-10-2022 08:00 - 19-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 16.10.2022
RQ107118 | 400KV BUS 1 AT CHITTORGARH(RS) | Approved | 19-10-2022 08:00 - 19-10-2022 18:00 | Could be taken on Daily Basis | FOR MAINTAINCE AND TESTING WORK | 16.10.2022
RQ104828 | 70652B MAIN BAY - 765KV ANTA-PHAGI (RS) CKT-1 AT PHAGI(RS) | Approved | 20-10-2022 08:00 - 20-10-2022 18:00 |  | HALF YEARLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 17.10.2022
RQ105561 | 220 KV RAPS_B(NP)-SAKATPURA(RS) (RS) CKT-1 | Approved | 20-10-2022 08:00 - 20-10-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 17.10.2022
RQ105570 | 220 KV CHARKHI DADRI(BB)-KHETRI(RS) (BB) CKT-2 | Approved | 20-10-2022 08:00 - 20-10-2022 18:00 |  | For quartely maintenance & Tree Trimming under the Line requiring Shutdown | 17.10.2022
RQ105572 | 220 KV RAPS_A(NP)-SAKATPURA(RS) (RS) CKT-2 | Approved | 21-10-2022 08:00 - 21-10-2022 18:00 |  | Quartly maintenance work and Testing of Equipment | 18.10.2022