## Sheet 1
S.N | Shutdown No | Element Name | RPC Status | RPC ShutDown Range | RPC Remarks | Reason | D-3 Req Date
1 | RQ122725 | 400 KV BASSI(PG)-HEERAPURA(RS) (PG) CKT-1 | Rejected |  | PG denied consent
2 | RQ122748 | 407 MAIN BAY - 400/220KV 250 MVA ICT 3 AT HEERAPURA(RS) | Approved | 01-03-2023 00:00 - 31-03-2023 18:00 | May be given subject to elements must remain in service via other bay | Shutdown id required from 21.02.2022 to 22.03.2022 but due to start date limitation in portal the same has been requested from 01.03.2022. Shutdown is required for replacement of 252 A CB by new CGL make CB. (one month shutdown) | 26.02.2023
3 | RQ122486 | 400 KV AKAL-KANKANI (RS) CKT-1 | Approved | 01-03-2023 08:00 - 01-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 26.02.2023
4 | RQ122351 | 400KV BUS 1 AT DEEDWANA(MTS) | Approved | 01-03-2023 08:00 - 01-03-2023 18:00 | May be given from 1700 Hrs | For annual preventive maintenance work | 26.02.2023
5 | RQ122727 | 400KV BUS 1 AT HEERAPURA(RS) | Approved | 01-03-2023 08:00 - 01-03-2023 18:00 | May be given from 1700 Hrs | For replacement of damaged Isolator (189 AA) of 400 KV Main Bus A. | 26.02.2023
6 | RQ122480 | 220 KV MODAK(RS)-BHANPURA(MP) (MPSEB) CKT-1 | Approved | 01-03-2023 08:00 - 13-03-2023 18:00 | All FTC procedures shall be followed. EI approval, PTCC approval to be submitted before charging of line. Subjected to WRPC Consent. | For shifting of 220 KV Modak- Bhanpura line due to construction of eight lane road under Bharatmala project as deposit work of NHAI(under supervision of RVPN) in the state of Rajasthan | 26.02.2023
7 | RQ122721 | 400 KV HEERAPURA-HINDAUN (RS) CKT-1 | Approved | 01-03-2023 08:00 - 16-03-2023 18:00 | Subject to Voltage management by Rajasthan and no other shutdown will be availed from both ends. | Modification & height raising work at tower location no. 307 & 308(Crossing of Delhi-Mumbai Express Highway) carried out by NHAI under Supervision of RVPNL. | 26.02.2023
8 | RQ122781 | 70152A MAIN BAY - 765KV PHAGI(RS)-BHIWANI(PG) (PG) CKT-2 AT PHAGI(RS) | Approved | 02-03-2023 08:00 - 02-03-2023 18:00 |  | 1. To check the operation timings of CB & measurement of contact resistance. 2. Measurement of Tan-delta of CTs. 3. Tightening of clamps & connectors. | 27.02.2023
9 | RQ122471 | 400 KV BIKANER(PG)-BIKANER(RS) (PG) CKT-2 | Approved | 02-03-2023 08:00 - 02-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 27.02.2023
10 | RQ122728 | 400KV BUS 2 AT HEERAPURA(RS) | Approved | 02-03-2023 08:00 - 02-03-2023 18:00 | May be given from 1700 Hrs | For replacement of damaged Isolator (189 AA) of 400 KV Main Bus B | 27.02.2023
11 | RQ122352 | 400KV BUS 2 AT DEEDWANA(MTS) | Approved | 02-03-2023 08:00 - 02-03-2023 18:00 | May be given from 1700 Hrs | For annual preventive maintenance work | 27.02.2023
12 | RQ122362 | 400/220 KV 315 MVA ICT 1 AT RATANGARH(RS) | Approved | 02-03-2023 08:00 - 02-03-2023 18:00 | May be given from 1700 Hrs | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 27.02.2023
13 | RQ125256 | 400 KV AKAL-KANKANI (RS) CKT-1 | Approved | 02-03-2023 08:00 - 02-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 27.02.2023
14 | RQ122379 | 50 MVAR BUS REACTOR NO 1 AT 400KV BIKANER(RS) | Approved | 03-03-2023 08:00 - 03-03-2023 18:00 |  | Routine Bay Maintenance Work | 28.02.2023
15 | RQ122780 | 70152B MAIN BAY - 765/400KV 1500 MVA ICT 1 AT PHAGI(RS) | Approved | 03-03-2023 08:00 - 03-03-2023 18:00 |  | 1. To check the operation timings of CB & measurement of contact resistance. 2. Measurement of Tan-delta of CTs. 3. Tightening of clamps & connectors. | 28.02.2023
16 | RQ122488 | 400 KV SURATGARH(RVUN)-BIKANER(RS) (RS) CKT-1 | Approved | 03-03-2023 08:00 - 03-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 28.02.2023
17 | RQ122472 | 400 KV KANKANI-JAISALMER (RS) CKT-2 | Approved | 03-03-2023 08:00 - 03-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 28.02.2023
18 | RQ122378 | 63 MVAR BUS REACTOR NO 2 AT 400 KV KAWAI SCTPS(APR) | Approved | 03-03-2023 08:00 - 04-03-2023 18:00 | May be given | Annual maintenance and testing of bus reactor#2 & Bay equipments. | 28.02.2023
19 | RQ122381 | 50 MVAR BUS REACTOR NO 1 AT 400KV RATANGARH(RS) | Approved | 04-03-2023 08:00 - 04-03-2023 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 01.03.2023
20 | RQ122778 | 70252B MAIN BAY - 765/400KV 1500 MVA ICT 2 AT PHAGI(RS) | Approved | 04-03-2023 08:00 - 04-03-2023 18:00 |  | 1. To check the operation timings of CB & measurement of contact resistance. 2. Measurement of Tan-delta of CTs. 3. Tightening of clamps & connectors. | 01.03.2023
21 | RQ125252 | 400 KV KANKANI-JAISALMER (RS) CKT-2 | Approved | 04-03-2023 08:00 - 04-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 01.03.2023
22 | RQ122345 | 400KV BUS 1 AT ALWAR(ATIL) | Approved | 06-03-2023 08:00 - 06-03-2023 18:00 | May be given from 1700 Hrs | For Annual maintenance testing | 03.03.2023
23 | RQ122502 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 06-03-2023 08:00 - 06-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 03.03.2023
24 | RQ122374 | 400/11 KV 80 MVA ST 1 AT KAWAI SCTPS(APR) | Approved | 06-03-2023 08:00 - 07-03-2023 18:00 | May be given | Annual maintenance and testing of station transformer#1 & bay equipments. | 03.03.2023
25 | RQ122498 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 06-03-2023 09:00 - 06-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 03.03.2023
26 | RQ125333 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 07-03-2023 08:00 - 07-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 04.03.2023
27 | RQ125245 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 07-03-2023 09:00 - 07-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 04.03.2023
28 | RQ122346 | 400KV BUS 2 AT ALWAR(ATIL) | Approved | 08-03-2023 08:00 - 08-03-2023 18:00 | May be given from 1700 Hrs | For Annual maintenance testing | 05.03.2023
29 | RQ122773 | 703B MAIN BAY - 765/400 KV 1500 MVA ICT 3 AT PHAGI(RS) (RRVPNL) AT 765 KV PHAGI(RS) | Approved | 08-03-2023 08:00 - 08-03-2023 18:00 |  | 1. To check the operation timings of CB & measurement of contact resistance. 2. Measurement of Tan-delta of CTs. 3. Tightening of clamps & connectors. | 05.03.2023
30 | RQ122492 | 400 KV KOTA(PG)-MERTA(RS) (PG) CKT-1 | Approved | 08-03-2023 08:00 - 08-03-2023 18:00 |  | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 05.03.2023
31 | RQ125334 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 08-03-2023 08:00 - 08-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 05.03.2023
32 | RQ125246 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 08-03-2023 09:00 - 08-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 05.03.2023
33 | RQ122491 | 220 KV INDIRA NAGAR(RS)-HEERAPURA(RS) (PG) CKT-1 | Approved | 08-03-2023 11:00 - 08-03-2023 17:00 |  | Quartererly maintenance of Bay Equipment | 05.03.2023
34 | RQ122405 | 400 KV ANTA-KALISINDH (RS) CKT-1 | Approved | 09-03-2023 08:00 - 09-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly and Quarterly Maintenance | 06.03.2023
35 | RQ122487 | 400 KV SHREE CEMENT(SCL)-MERTA(RS) (PG) CKT-1 | Approved | 09-03-2023 08:00 - 09-03-2023 18:00 |  | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 06.03.2023
36 | RQ125335 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 09-03-2023 08:00 - 09-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 06.03.2023
37 | RQ122416 | 400KV BUS 1 AT KAWAI SCTPS(APR) | Approved | 09-03-2023 08:00 - 10-03-2023 18:00 | May be given subject to all elements must remain in service via other BUS | Annual maintenance & testing of 400 KV Bus - 1 & connecting isolators. | 06.03.2023
38 | RQ125247 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 09-03-2023 09:00 - 09-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 06.03.2023
39 | RQ122499 | 400 KV BIKANER-MERTA (RS) CKT-1 | Approved | 10-03-2023 08:00 - 10-03-2023 18:00 | Shutdown May be given from 1700 Hrs | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS alongwith 50MVAR line Reactor-III at merta | 07.03.2023
40 | RQ122500 | 400 KV JODHPUR-KANKANI (RS) CKT-1 | Approved | 10-03-2023 08:00 - 10-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 07.03.2023
41 | RQ122393 | 400 KV ANTA-CHHABRA SCTPS (RS) CKT-1 | Approved | 10-03-2023 08:00 - 10-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly and Quarterly Maintenance | 07.03.2023
42 | RQ122726 | 400 KV BASSI(PG)-HEERAPURA(RS) (PG) CKT-2 | Approved | 10-03-2023 08:00 - 10-03-2023 18:00 |  | Testing work of 400 KV side bay Equipments | 07.03.2023
43 | RQ122779 | 70252A MAIN BAY - 765 KV PHAGI(RS)-BHIWANI(PG) (PG) CKT-1 AT PHAGI(RS) | Approved | 10-03-2023 08:00 - 10-03-2023 18:00 |  | 1. To check the operation timings of CB & measurement of contact resistance. 2. Measurement of Tan-delta of CTs. 3. Tightening of clamps & connectors. | 07.03.2023
44 | RQ125336 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 10-03-2023 08:00 - 10-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 07.03.2023
45 | RQ125248 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 10-03-2023 09:00 - 10-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 07.03.2023
46 | RQ122489 | 400 KV SURATGARH(RVUN)-RATANGARH(RS) (RS) CKT-1 | Approved | 11-03-2023 08:00 - 11-03-2023 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 08.03.2023
47 | RQ122373 | 400/220 KV 315 MVA ICT 1 AT MERTA(RS) | Approved | 11-03-2023 08:00 - 11-03-2023 18:00 | May be given from 1700 Hrs | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 08.03.2023
48 | RQ122392 | 400 KV SURATGARH SCTPS(RVUN)-BIKANER(RS) (RS) CKT-1 | Approved | 11-03-2023 08:00 - 11-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Annual Outage works (Hardware Correction, Insulator replacement & Counter weight installation) | 08.03.2023
49 | RQ125233 | 400 KV JODHPUR-KANKANI (RS) CKT-1 | Approved | 11-03-2023 08:00 - 11-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 08.03.2023
50 | RQ125337 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 11-03-2023 08:00 - 11-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 08.03.2023
51 | RQ125249 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 11-03-2023 09:00 - 11-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 08.03.2023
52 | RQ125338 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 12-03-2023 08:00 - 12-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 09.03.2023
53 | RQ125250 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 12-03-2023 09:00 - 12-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 09.03.2023
54 | RQ122775 | 70552A MAIN BAY - 240 MVAR BUS REACTOR NO 1 AT 765KV PHAGI(RS) | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 |  | 1.Measurement of tan-delta of CTs 2. Maintenance of CB & CTs. 3. Tightening of clamps & connectors. | 10.03.2023
55 | RQ122735 | 400/220 KV 250 MVA ICT 1 AT HEERAPURA(RS) | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 | May be given from 1700 Hrs | Testing work of 400 KV & 220 KV side bay Equipments | 10.03.2023
56 | RQ122360 | 400/220 KV 315 MVA ICT 2 AT MERTA(RS) | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 | May be given from 1700 Hrs | QUARTERLY MAINT.WORK OF BAY & EQUIPMENTS | 10.03.2023
57 | RQ122365 | 400/220 KV 315 MVA ICT 2 AT BHILWARA(RS) | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 | May be given from 1700 Hrs | Routine maintenance and testing of 315 MVA 400/220/33 KV ICT No.-2 & ASSOCIATED 400KV & 220KV BAY EQUIPMENTS | 10.03.2023
58 | RQ122485 | 400 KV MERTA-KANKANI (RS) CKT-1 | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 10.03.2023
59 | RQ122397 | 400 KV ANTA-CHHABRA (RS) CKT-1 | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly and Quarterly Maintenance | 10.03.2023
60 | RQ122495 | 400 KV AKAL-RAMGARH (RS) CKT-1 | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 |  | Quarterly Maintenance | 10.03.2023
61 | RQ125339 | 400 KV BIKANER(PG)-BHADLA(RS) (PG) CKT-1 | Approved | 13-03-2023 08:00 - 13-03-2023 18:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 10.03.2023
62 | RQ122403 | 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-1 | Approved | 13-03-2023 08:00 - 14-03-2023 18:00 | may be given on daily basis | 1. Calibration of line metering CT | 10.03.2023
63 | RQ125251 | 400 KV BIKANER-BHADLA (RS) CKT-1 | Approved | 13-03-2023 09:00 - 13-03-2023 17:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 10.03.2023
64 | RQ123103 | 400KV BUS 2 AT BHILWARA(RS) | Approved | 14-03-2023 08:00 - 14-03-2023 18:00 | May be given from 1700 Hrs | Yearly Maintenance of 400KV Main Bus-2 and Associated Equipments | 11.03.2023
65 | RQ122490 | 400 KV SURATGARH(RVUN)-RATANGARH(RS) (RS) CKT-2 | Approved | 14-03-2023 08:00 - 14-03-2023 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 11.03.2023
66 | RQ122400 | 400 KV AJMER-BHILWARA (RS) CKT-1 | Approved | 14-03-2023 08:00 - 14-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly maintenance work of associated equipments of 400 kV Ajmer-Bhilwara -I Line & Bay (401) & TIE bay 400 KV Ajmer-Bhilwara Ckt-I (402) | 11.03.2023
67 | RQ122734 | 400/220 KV 250 MVA ICT 2 AT HEERAPURA(RS) | Approved | 14-03-2023 08:00 - 14-03-2023 18:00 | May be given from 1700 Hrs | Testing work of 400 KV & 220 KV side bay Equipments | 11.03.2023
68 | RQ122776 | 70752B MAIN BAY - 765KV ANTA-PHAGI (RS) CKT-2 AT PHAGI(RS) | Approved | 14-03-2023 08:00 - 14-03-2023 18:00 |  | 1.Measurement of tan-delta of CTs 2. Maintenance of CB & CTs. 3. Tightening of clamps & connectors. | 11.03.2023
69 | RQ125229 | 400 KV MERTA-KANKANI (RS) CKT-1 | Approved | 14-03-2023 08:00 - 14-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 11.03.2023
70 | RQ122476 | 400 KV BHADLA(RS)-BHADLA(PG) (PG) CKT-1 | Approved | 14-03-2023 17:00 - 14-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For half yearly/ yearly maintenance work | 11.03.2023
71 | RQ122774 | 70552B MAIN BAY - 765 KV AJMER(PG)-PHAGI(RS) (PAPTL) CKT-1 (PAPTL) AT 765 KV PHAGI(RS) | Approved | 15-03-2023 08:00 - 15-03-2023 18:00 |  | 1. Maintenance of CB & CTs 2. Tightening of clamps & connectors of Isolators, CB & CTs. | 12.03.2023
72 | RQ122501 | 400 KV JODHPUR-KANKANI (RS) CKT-2 | Approved | 15-03-2023 08:00 - 15-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 12.03.2023
73 | RQ122494 | 220 KV ANTA(NT)-BHILWARA(RS) (PG) CKT-1 | Approved | 15-03-2023 08:00 - 15-03-2023 18:00 |  | Routine Maintenance of Bay & Line | 12.03.2023
74 | RQ122731 | 400/220 KV 250 MVA ICT 3 AT HEERAPURA(RS) | Approved | 15-03-2023 08:00 - 15-03-2023 18:00 | May be given from 1700 Hrs | Testing work of 400 KV & 220 KV side bay Equipments | 12.03.2023
75 | RQ122404 | 400 KV ANTA(RS)-KAWAI SCTPS(APR) (RS) CKT-2 | Approved | 15-03-2023 08:00 - 16-03-2023 18:00 | may be given on daily basis | 1. Calibration of line metering CT | 12.03.2023
76 | RQ122496 | 400 KV AKAL-RAMGARH (RS) CKT-2 | Approved | 15-03-2023 17:00 - 15-03-2023 18:00 |  | Quarterly Maintenance | 12.03.2023
77 | RQ122401 | 400 KV AJMER-BHILWARA (RS) CKT-2 | Approved | 15-03-2023 17:00 - 15-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly maintenance work of associated equipments of 400 kV Ajmer-Bhilwara -II Line & Bay (404) & TIE bay 400 KV Ajmer-Bhilwara Ckt-II (405) | 12.03.2023
78 | RQ122477 | 400 KV BHADLA(RS)-BHADLA(PG) (PG) CKT-2 | Approved | 15-03-2023 17:00 - 15-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For half yearly/ yearly maintenance work | 12.03.2023
79 | RQ122349 | 400KV BUS 1 AT BIKANER(RS) | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 13.03.2023
80 | RQ122371 | 765/400 KV 1500 MVA ICT 1 AT PHAGI(RS) | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 |  | 1. Testing and maintenance of Transforers. 2. Tightening of clamps and connectors | 13.03.2023
81 | RQ122736 | 400/220 KV 315 MVA ICT 4 AT HEERAPURA(RS) | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 | May be given from 1700 Hrs | Testing work of 400 KV & 220 KV side bay Equipments | 13.03.2023
82 | RQ122377 | 400/220 KV 500 MVA ICT 1 AT BHILWARA(RS) | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 | May be given from 1700 Hrs | outine Maintenance and Testing of 500 MVA 400/220/33 KV Transformer No.1 and Bay (4152A) & Associated Equipments | 13.03.2023
83 | RQ122363 | 400/220 KV 315 MVA ICT 2 AT RATANGARH(RS) | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 | May be given from 1700 Hrs | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 13.03.2023
84 | RQ122396 | 132 KV AMARPURATHEDI(RS)-HISAR(BB) (RS) CKT-1 | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 |  | for Line Maintenance | 13.03.2023
85 | RQ125228 | 400 KV JODHPUR-KANKANI (RS) CKT-2 | Approved | 16-03-2023 08:00 - 16-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 13.03.2023
86 | RQ122372 | 765/400 KV 1500 MVA ICT 2 AT ANTA(RS) | Approved | 16-03-2023 08:00 - 17-03-2023 18:00 |  | HALF YEARLY MAINTENANCE & TESTING WORK | 13.03.2023
87 | RQ122503 | 400 KV SURATGARH SCTPS(RVUN)-BIKANER(RS) (RS) CKT-2 | Approved | 16-03-2023 17:00 - 16-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 13.03.2023
88 | RQ122473 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | Approved | 16-03-2023 17:00 - 16-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 13.03.2023
89 | RQ122398 | 400 KV AJMER(RS)-AJMER(PG) (PG) CKT-1 | Approved | 16-03-2023 17:00 - 16-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly maintenance work of associated equipments of 400 KV Ajmer-Ajmer (PG) Ckt-I Line & Bay (422) & TIE bay 400 KV Ajmer-Ajmer (PG) Ckt-I (423) to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 13.03.2023
90 | RQ122369 | 400/220 KV 315 MVA ICT 1 AT BIKANER(RS) | Approved | 17-03-2023 08:00 - 17-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 14.03.2023
91 | RQ122777 | 70652A MAIN BAY - 765KV PHAGI(RS)-GWALIOR(PG) (UNDEF) CKT-1 AT PHAGI(RS) | Approved | 17-03-2023 08:00 - 17-03-2023 18:00 |  | 1. Testing and maintenance of Transforers. 2. Tightening of clamps and connectors | 14.03.2023
92 | RQ122724 | 400 KV ALWAR(ATIL)-HINDAUN(RS) (ATIL) CKT-1 | Approved | 17-03-2023 08:00 - 17-03-2023 18:00 |  | Annual Outage works (Hardware Correction, Insulator replacement & Counter weight installation) | 14.03.2023
93 | RQ122399 | 400 KV AJMER(RS)-AJMER(PG) (PG) CKT-2 | Approved | 17-03-2023 17:00 - 17-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly maintenance work of associated equipments of 400 KV Ajmer-Ajmer (PG) Ckt-II Line & Bay (419) & TIE bay 400 KV Ajmer-Ajmer (PG) Ckt-II (420) to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 14.03.2023
94 | RQ122719 | 400 KV PHAGI-HEERAPURA (RS) CKT-1 | Approved | 17-03-2023 17:00 - 17-03-2023 18:00 | may be given from 1700 Hrs | Testing work of 400 KV side bay Equipments | 14.03.2023
95 | RQ122478 | 400 KV BHADLA-RAMGARH (RS) CKT-1 | Approved | 17-03-2023 17:00 - 17-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Quarterly Maintenance with Reactor (50 MVAR Line Reactor) | 14.03.2023
96 | RQ122474 | 400 KV RAJWEST(RW)-KANKANI (RS) CKT-1 | Approved | 17-03-2023 17:00 - 17-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 14.03.2023
97 | RQ122722 | 400 KV HINDAUN(RS)-CHHABRA(RVUN) (RS) CKT-1 | Approved | 17-03-2023 17:00 - 21-03-2023 18:00 | Subject to Voltage management by Rajasthan and no other shutdown will be availed from both ends. | For shifting of line from 05 Nos. ERS Towers to Conventional towers at Loc. No. 359 & 362 | 14.03.2023
98 | RQ122389 | 765 KV AJMER(PG)-PHAGI(RS) (PAPTL) CKT-1 | Approved | 18-03-2023 08:00 - 18-03-2023 18:00 |  | Maitenance of line bay equipments i.e. CVT, WT, LA & line Isolator. | 15.03.2023
99 | RQ122367 | 400/220 KV 315 MVA ICT 3 AT RATANGARH(RS) | Approved | 18-03-2023 08:00 - 18-03-2023 18:00 | May be given from 1700 Hrs | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 15.03.2023
100 | RQ125269 | 400 KV ALWAR(ATIL)-HINDAUN(RS) (ATIL) CKT-1 | Approved | 18-03-2023 08:00 - 18-03-2023 18:00 |  | Annual Outage works (Hardware Correction, Insulator replacement & Counter weight installation) | 15.03.2023
101 | RQ122482 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 18-03-2023 16:00 - 18-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 15.03.2023
102 | RQ122720 | 400 KV PHAGI-HEERAPURA (RS) CKT-2 | Approved | 18-03-2023 17:00 - 18-03-2023 18:00 | may be given from 1700 Hrs | Testing work of 400 KV side bay Equipments | 15.03.2023
103 | RQ125227 | 400 KV RAJWEST(RW)-KANKANI (RS) CKT-1 | Approved | 18-03-2023 17:00 - 18-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 15.03.2023
104 | RQ122481 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 18-03-2023 17:00 - 18-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 15.03.2023
105 | RQ125219 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 19-03-2023 16:00 - 19-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 16.03.2023
106 | RQ122479 | 400 KV BHADLA-RAMGARH (RS) CKT-2 | Approved | 19-03-2023 17:00 - 19-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Quarterly Maintenance with Reactor (50 MVAR Line Reactor) | 16.03.2023
107 | RQ125211 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 19-03-2023 17:00 - 19-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 16.03.2023
108 | RQ122364 | 765/400 KV 1500 MVA ICT 2 AT PHAGI(RS) | Approved | 20-03-2023 08:00 - 20-03-2023 18:00 |  | 1. Testing and maintenance of Transforers. 2. Tightening of clamps and connectors | 17.03.2023
109 | RQ122375 | 400/220 KV 315 MVA ICT 1 AT KANKANI(RS) | Approved | 20-03-2023 08:00 - 20-03-2023 18:00 | May be given from 1700 Hrs | Preventive maintenance & Testing of bay and equipments | 17.03.2023
110 | RQ122370 | 765/400 KV 1500 MVA ICT 3 AT ANTA(RS) | Approved | 20-03-2023 08:00 - 21-03-2023 18:00 |  | HALF YEARLY MAINTENANCE & TESTING WORK | 17.03.2023
111 | RQ122747 | 414 TIE BAY - 400KV CHHABRA(RVUN)-KAWAI SCTPS(APR) (RS) CKT-1 AND FUTURE AT KAWAI SCTPS(APR) | Approved | 20-03-2023 08:00 - 22-03-2023 18:00 | may be given from 1500 Hrs subject to ckt must remain in service | Circuit Breaker Overhauling | 17.03.2023
112 | RQ125220 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 20-03-2023 16:00 - 20-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 17.03.2023
113 | RQ122483 | 400 KV BHILWARA-CHITTORGARH (RS) CKT-1 | Approved | 20-03-2023 17:00 - 20-03-2023 18:00 | may be given from 1700 Hrs | Yearly maintenance work of associated equipments of 400 kV Bhilwara -Chitor Ckt-1 Line & Bay (4252B) & TIE bay 400 kV Bhilwara -Chitor Ckt-1 Line (4252T) | 17.03.2023
114 | RQ122723 | 400 KV MERTA-HEERAPURA (RS) CKT-1 | Approved | 20-03-2023 17:00 - 20-03-2023 18:00 |  | Testing work of 400 KV side bay Equipments | 17.03.2023
115 | RQ125212 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 20-03-2023 17:00 - 20-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 17.03.2023
116 | RQ122384 | 50 MVAR BUS REACTOR NO 1 AT 400KV BIKANER(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 |  | Routine Bay Maintenance Work | 18.03.2023
117 | RQ122798 | 410 MAIN BAY - 400 KV BASSI(PG)-PHAGI(RS) (PG) CKT-2 AT PHAGI(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 |  | Quarterly mainttenance work | 18.03.2023
118 | RQ122350 | 400KV BUS 2 AT BIKANER(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 18.03.2023
119 | RQ122344 | 400KV BUS 2 AT AJMER(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly maintenance work of associated equipments of 400 KV Main Bus-II to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 18.03.2023
120 | RQ122356 | 400KV BUS 1 AT RATANGARH(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 | May be given from 1700 Hrs | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 18.03.2023
121 | RQ122361 | 400/220 KV 500 MVA ICT 2 AT RAMGARH(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 | May be given from 1700 Hrs | Quarterly maintenance | 18.03.2023
122 | RQ122368 | 400/220 KV 315 MVA ICT 3 AT AJMER(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly maintenance work of associated equipments of 400/220 kV, 315 MVA ICT-III Bay to be carried out by M/s Suncity urja pvt. Ltd. Jaipur | 18.03.2023
123 | RQ122739 | 125 MVAR BUS REACTOR NO 1 AT 400KV HINDAUN(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 |  | For Yearly Maintenance & testing Work | 18.03.2023
124 | RQ124729 | 400/220 KV 315 MVA ICT 1 AT KANKANI(RS) | Approved | 21-03-2023 08:00 - 21-03-2023 18:00 | May be given from 1700 Hrs | Preventive maintenance & Testing of bay and equipments | 18.03.2023
125 | RQ125221 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 21-03-2023 16:00 - 21-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 18.03.2023
126 | RQ122504 | 400 KV SURATGARH(RVUN)-BIKANER(RS) (RS) CKT-1 | Approved | 21-03-2023 17:00 - 21-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Routine Bay Maintenance Work | 18.03.2023
127 | RQ122484 | 400 KV BHILWARA-CHITTORGARH (RS) CKT-2 | Approved | 21-03-2023 17:00 - 21-03-2023 18:00 | may be given from 1700 Hrs | 1. Routine maintenance and testing work of associated equipments of 400 kV Bhilwara -Chitor Ckt-2 Line & Bay (4152B) & TIE bay400 kV Bhilwara -Chitor Ckt-1 (4152T) 2.Carrier protection wiring and testing as desired by PLCC wing. | 18.03.2023
128 | RQ125213 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 21-03-2023 17:00 - 21-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 18.03.2023
129 | RQ122376 | 400/220 KV 500 MVA ICT 2 AT KANKANI(RS) | Approved | 22-03-2023 08:00 - 22-03-2023 18:00 | May be given from 1700 Hrs | Preventive maintenance & Testing of bay and equipments | 19.03.2023
130 | RQ122729 | 400KV BUS 1 AT HINDAUN(RS) | Approved | 22-03-2023 08:00 - 22-03-2023 18:00 | May be given from 1700 Hrs | For Yearly Maintenance & testing Work | 19.03.2023
131 | RQ122799 | 407 MAIN BAY - 400 KV BASSI(PG)-PHAGI(RS) (PG) CKT-1 AT PHAGI(RS) | Approved | 22-03-2023 08:00 - 22-03-2023 18:00 |  | Quarterly mainttenance work | 19.03.2023
132 | RQ125222 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 22-03-2023 16:00 - 22-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 19.03.2023
133 | RQ122391 | 400 KV AJMER(RS)-DEEDWANA(MTS) (RS) CKT-1 | Approved | 22-03-2023 17:00 - 22-03-2023 18:00 | may be given from 1700 Hrs | Annual Outage works (Hardware Correction, Insulator replacement & Counter weight installation) at Both end. | 19.03.2023
134 | RQ122497 | 400 KV BHILWARA(RS)-CHHABRA(RVUN) (RS) CKT-1 | Approved | 22-03-2023 17:00 - 22-03-2023 18:00 | may be given from 1700 Hrs | Yearly Maintenance of 400 KV CHHABRA LINE Bay ( 4352A ) with 50MVAR Reactor & BAY & ASSOCIATED EQUIPMENTS | 19.03.2023
135 | RQ125214 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 22-03-2023 17:00 - 22-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 19.03.2023
136 | RQ122366 | 400/220 KV 500 MVA ICT 1 AT RAMGARH(RS) | Approved | 23-03-2023 08:00 - 23-03-2023 18:00 | May be given from 1700 Hrs | Quarterly Maintenance | 20.03.2023
137 | RQ122797 | 40752C MAIN BAY - 765/400KV 1500 MVA ICT 1 AT PHAGI(RS) | Approved | 23-03-2023 08:00 - 23-03-2023 18:00 |  | QUARTERLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 20.03.2023
138 | RQ124728 | 400/220 KV 500 MVA ICT 2 AT KANKANI(RS) | Approved | 23-03-2023 08:00 - 23-03-2023 18:00 | May be given from 1700 Hrs | Preventive maintenance & Testing of bay and equipments | 20.03.2023
139 | RQ122746 | 409 MAIN BAY - 63 MVAR BUS REACTOR NO 2 AT 400 KV KAWAI SCTPS(APR) | Approved | 23-03-2023 08:00 - 26-03-2023 18:00 | May be given subject to elements must remain in service via other bay | Circuit Breaker Overhauling | 20.03.2023
140 | RQ125223 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 23-03-2023 16:00 - 23-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 20.03.2023
141 | RQ125215 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 23-03-2023 17:00 - 23-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 20.03.2023
142 | RQ122358 | 400KV BUS 1KANKANI(RS) | Approved | 24-03-2023 08:00 - 24-03-2023 18:00 | May be given from 1700 Hrs | Preventive maintenance & Testing of bay and equipments | 21.03.2023
143 | RQ122794 | 40552T TIE BAY - 400KV BASSI(PG)-PHAGI(RS) (PG) CKT-1 AND FUTURE AT PHAGI(RS) | Approved | 24-03-2023 08:00 - 24-03-2023 18:00 |  | QUARTERLY MAINTENANCE WORK OF ASSOCITED BAY EQUIPMENTS | 21.03.2023
144 | RQ122730 | 400KV BUS 2 AT HINDAUN(RS) | Approved | 24-03-2023 08:00 - 24-03-2023 18:00 | May be given from 1700 Hrs | For Yearly Maintenance & testing Work | 21.03.2023
145 | RQ125224 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 24-03-2023 16:00 - 24-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 21.03.2023
146 | RQ122395 | 400 KV ANTA(RS)-KOTA(PG) (RS) CKT-1 | Approved | 24-03-2023 17:00 - 24-03-2023 18:00 | may be given from 1700 Hrs | Half Yearly and Quarterly Maintenance | 21.03.2023
147 | RQ122390 | 400 KV BIKANER(RS)-DEEDWANA(MTS) (RS) CKT-1 | Approved | 24-03-2023 17:00 - 24-03-2023 18:00 | Shutdown May be given from 1700 Hrs | Annual Outage works (Hardware Correction, Insulator replacement & Counter weight installation) | 21.03.2023
148 | RQ125216 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 24-03-2023 17:00 - 24-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 21.03.2023
149 | RQ122354 | 400KV BUS 1 AT RAMGARH(RS) | Approved | 25-03-2023 08:00 - 25-03-2023 18:00 |  | Quarterly Maintenance | 22.03.2023
150 | RQ122359 | 400KV BUS 2KANKANI(RS) | Approved | 25-03-2023 08:00 - 25-03-2023 18:00 | May be given from 1700 Hrs | Preventive maintenance & Testing of bay and equipments | 22.03.2023
151 | RQ122357 | 400KV BUS 2 AT RATANGARH(RS) | Approved | 25-03-2023 08:00 - 25-03-2023 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 22.03.2023
152 | RQ122796 | 40752D MAIN BAY - 400KV PHAGI-HEERAPURA (RS) CKT-2 AT PHAGI(RS) | Approved | 25-03-2023 08:00 - 25-03-2023 18:00 |  | QUARTERLY MAINTENANCE WORK OF MAIN BAY EQUIPMENTS OF 400KV PHAGI-HEERAPURA LINE-2 | 22.03.2023
153 | RQ125225 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 25-03-2023 16:00 - 25-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 22.03.2023
154 | RQ125217 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 25-03-2023 17:00 - 25-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 22.03.2023
155 | RQ125226 | 400 KV BHADLA-MERTA (RS) CKT-1 | Approved | 26-03-2023 16:00 - 26-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 23.03.2023
156 | RQ125218 | 400 KV BHADLA-JODHPUR (RS) CKT-1 | Approved | 26-03-2023 17:00 - 26-03-2023 22:00 | Shutdown May be given from 1700 Hrs | For Tightening of jumper, Missing , Loosening Nut Bolts at various Locations | 23.03.2023
157 | RQ122382 | 80 MVAR BUS REACTOR NO 1 AT 400 KV KANKANI(RS) | Approved | 27-03-2023 08:00 - 27-03-2023 18:00 |  | Preventive maintenance & Testing of bay and equipments | 24.03.2023
158 | RQ122406 | 400 KV ANTA-KALISINDH (RS) CKT-2 | Approved | 27-03-2023 08:00 - 27-03-2023 18:00 | may be given from 1700 Hrs | For Halfyearly Maintenance and Installation of Repaired DISTANCE PROTECTION MAIN -1 Relay (ABB Make) | 24.03.2023
159 | RQ122355 | 400KV BUS 2 AT RAMGARH(RS) | Approved | 27-03-2023 08:00 - 27-03-2023 18:00 |  | Quarterly Maintenance | 24.03.2023
160 | RQ122732 | 400/220 KV 315 MVA ICT 1 AT HINDAUN(RS) | Approved | 27-03-2023 08:00 - 27-03-2023 18:00 | May be given from 1700 Hrs | For Yearly Maintenance & testing Work | 24.03.2023
161 | RQ122353 | 765KV BUS 1 AT PHAGI(RS) | Approved | 27-03-2023 08:00 - 27-03-2023 18:00 | Bypass arrangement to be done at Anta for Chabra-Anta-Kota line. Generation at Chabra Kawai Complex to be restricted to 3500 MW/Subject to real time consent of Rajasthan | QUARTERLY MAINTENANCE WORK OF associated EQUIPMENTS of 765 KV Main Bus-I | 24.03.2023
162 | RQ122394 | 400 KV ANTA-CHHABRA SCTPS (RS) CKT-2 | Approved | 28-03-2023 08:00 - 28-03-2023 18:00 | may be given from 1700 Hrs | For Halfyearly Maintenance and Installation of Repaired DISTANCE PROTECTION MAIN -1 Relay (ABB Make) | 25.03.2023
163 | RQ122733 | 400/220 KV 315 MVA ICT 2 AT HINDAUN(RS) | Approved | 28-03-2023 08:00 - 28-03-2023 18:00 | May be given from 1700 Hrs | For Yearly Maintenance & testing Work | 25.03.2023
164 | RQ122787 | 70652B MAIN BAY - 765KV ANTA-PHAGI (RS) CKT-1 AT PHAGI(RS) | Approved | 28-03-2023 08:00 - 28-03-2023 18:00 |  | QUARTERLY MAINTENANCE WORK OF MAIN BAY EQUIPMENTS OF 765KV PHAGI-ANTA LINE-1 | 25.03.2023
165 | RQ122493 | 400 KV MERTA-RATANGARH (RS) CKT-1 | Approved | 28-03-2023 08:00 - 28-03-2023 18:00 |  | Maintenance work of bay equipments , isolators and testing work of bay equipments. | 25.03.2023
166 | RQ122786 | 70752A MAIN BAY - 765KV PHAGI(RS)-GWALIOR(PG) (UNDEF) CKT-2 AT PHAGI(RS) | Approved | 29-03-2023 08:00 - 29-03-2023 18:00 |  | QUARTERLY MAINTENANCE WORK OF MAIN BAY EQUIPMENTS OF 765KV PHAGI-Gwaliar LINE-2 | 26.03.2023
167 | RQ122408 | 765 KV ANTA-PHAGI (RS) CKT-2 | Approved | 29-03-2023 08:00 - 29-03-2023 18:00 |  | For Halfyearly Maintenance and Installation of Repaired DISTANCE PROTECTION MAIN -1 Relay (ABB Make) along with 3*80 MVAR Line Reactor Bank-II | 26.03.2023
168 | RQ122380 | 125 MVAR BUS REACTOR NO 1 AT 400KV RAMGARH(RS) | Approved | 29-03-2023 08:00 - 29-03-2023 18:00 |  | Quarterly maintenance | 26.03.2023
169 | RQ122795 | 40852D MAIN BAY - 400KV PHAGI-AJMER (RS) CKT-2 AT PHAGI(RS) | Approved | 30-03-2023 08:00 - 30-03-2023 18:00 | may be given from 1500 Hrs subject to ckt must remain in service | QUARTERLY MAINTENANCE WORK OF MAIN BAY EQUIPMENTS OF 400KV PHAGI-AJMER LINE-2 | 27.03.2023
170 | RQ122383 | 400/220 KV 500 MVA ICT 3 AT RAMGARH(RS) | Approved | 30-03-2023 08:00 - 30-03-2023 18:00 | May be given from 1700 Hrs | Quarterly maintenance | 27.03.2023
171 | RQ122800 | 419 MAIN BAY - 765/400KV 1500 MVA ICT 2 AT PHAGI(RS) | Approved | 31-03-2023 08:00 - 31-03-2023 18:00 |  | QUARTERLY MAINTENANCE WORK OF MAIN BAY EQUIPMENTS | 28.03.2023